## Sheet1
Task Name | Assignee | Task Status | Expected time to finish | Actual time to finish
DIO | Mahmoud Sarhan | Completed | 2 | 2.5
Timer | Mohammed Abdel-Wahab | Completed | 2.5 | 2
Ext_int | Arafa Arafa | Completed | 2 | 3
Car_control | basel nagy | Completed | 5 | 6
Timer_manager | Mohammed Abdel-Wahab | Completed | 2 | 3
Ext_int_manager | Arafa Arafa | Completed | 2 | 2
LED | Mahmoud Sarhan | Completed | 1 | 1
BUTTON | Mahmoud Sarhan | Completed | 2 | 2
motor | basel nagy | Completed | 2 | 2
APP | Mahmoud Sarhan | Completed | 8 | 5